DATANEXUS

90-DAY LAUNCH PLAN

Day-by-day execution plan: cluster build → governance → blockchain → AI → launch

Guided by the Manifest  ·  Enforced by Six Sigma  ·  Built on Hadoop

HOW TO USE THIS PLAN

Each week has specific deliverables. Each phase has a milestone. No week ends without the milestone task completed — if it slips, everything slips. The Six Sigma phase shown on each week is the DMAIC discipline that week primarily exercises. All tasks are real: commands, hires, customer calls, and code — not abstractions.

PHASE 1  Core Hadoop Cluster

Days 1–30  ·  Months 1–2

Goal: 5-node Hadoop cluster running — Spark, Kafka, Airflow, NiFi, Presto. Replaces AWS EMR + Kinesis + Glue + Athena combined. Zero cloud dependency.

WEEK 1 — Environment & HDFS  ·  Six Sigma: Define

Provision 5 Ubuntu 22.04 machines (bare metal or on-prem VMs): 1 NameNode, 4 DataNodes, minimum 32GB RAM each

Install Java 11 on all nodes: sudo apt install openjdk-11-jdk

Create 'hadoop' user, configure passwordless SSH between all nodes

Download Hadoop 3.3.6: wget https://downloads.apache.org/hadoop/common/hadoop-3.3.6/hadoop-3.3.6.tar.gz

Configure hdfs-site.xml (replication=3), core-site.xml, yarn-site.xml on all nodes

Format NameNode: hdfs namenode -format

Start HDFS: start-dfs.sh — verify all DataNodes registered at http://namenode:9870

Create base directory structure: hdfs dfs -mkdir -p /datanexus/raw /datanexus/curated /datanexus/exports

Run baseline write/read test: 1GB file upload to HDFS — record throughput as Day 1 benchmark

▸ MILESTONE: HDFS cluster running, all 4 DataNodes registered, benchmark recorded

WEEK 2 — Spark + YARN  ·  Six Sigma: Define

Install Apache Spark 3.5 on all nodes: configure spark-env.sh with YARN as resource manager

Set HADOOP_CONF_DIR to point Spark to YARN — test: spark-submit --master yarn pi.py

Configure executor memory (16GB), driver memory (4GB), dynamic allocation enabled

Install PySpark: pip install pyspark — write first DataNexus ingestion job in Python

Build and run test pipeline: read CSV from HDFS → transform with Spark → write Parquet back to HDFS

Verify YARN resource manager at http://namenode:8088 — all containers reporting

Install Apache Spark History Server — enable event logging for debugging

Run Spark performance benchmark: 10M row aggregation — record time as baseline sigma metric

▸ MILESTONE: Spark running on YARN — first DataNexus transformation pipeline executed end to end

WEEK 3 — Kafka + NiFi (Streaming Ingestion)  ·  Six Sigma: Measure

Install Apache Kafka 3.6 on 3 dedicated broker nodes — configure ZooKeeper quorum

Create first topic: kafka-topics.sh --create --topic datanexus.raw.ingest --partitions 12 --replication-factor 3

Install Apache NiFi 1.23 on master node — access UI at https://master:8443/nifi

Build NiFi flow: REST API source → JSON parse → Kafka publish → HDFS sink (drag-drop, no code)

Configure NiFi to ingest from 3 sample sources: REST API, CSV files, Postgres database via JDBC

Write Kafka consumer in PySpark Structured Streaming — reads from topic, writes to HDFS Parquet

Install Apache Sqoop for RDBMS bulk import — test: sqoop import from MySQL to HDFS

Run 24-hour streaming test — measure throughput, lag, and data loss (target: zero loss)

▸ MILESTONE: Streaming pipeline live — data flowing from 3 sources through Kafka into HDFS continuously

WEEK 4 — Airflow + Presto (Orchestration + Query)  ·  Six Sigma: Measure

Install Apache Airflow 2.8 with PostgreSQL backend — configure celery executor for distributed tasks

Write first DataNexus DAG: daily_ingest_pipeline — Kafka → HDFS → Spark transform → Hive load

Schedule DAG at 2AM daily — configure SLA alerts (email + Slack) if job exceeds 90 minutes

Install Apache Hive 3.1 — create first external table over HDFS Parquet data

Install Presto (Trino 435) — configure Hive connector, HDFS connector

Run first federated query: join HDFS data with external MySQL via single Presto SQL — no ETL

Install Apache Iceberg — migrate first Hive table to Iceberg format for ACID + time travel

Full end-to-end test: REST API → NiFi → Kafka → HDFS → Spark → Hive/Iceberg → Presto query — single pipeline

▸ MILESTONE: Full Phase 1 stack operational — investor demo pipeline ready to show

PHASE 2  Governance, Security & Quality

Days 31–45  ·  Month 3

Goal: Atlas metadata catalog, Ranger security, Great Expectations quality testing — DPDP Act compliance automatic from day one of this phase.

WEEK 5 — Atlas + Ranger (Catalog & Security)  ·  Six Sigma: Define + Control

Install Apache Atlas 2.3 — configure Kafka hook for automatic Hive/Spark lineage capture

Verify: run Spark job and check that Atlas automatically creates input/output lineage entities

Tag all existing HDFS datasets in Atlas with owner, classification (PII/financial/public), and retention policy

Install Apache Ranger 2.4 — connect to HDFS, Hive, Kafka, and HBase for centralized policy management

Create PII masking policy: Ranger masks Aadhaar and PAN columns for all users except data owners

Create row-level security policy: sales team sees only their region's data — no code change needed

Test DPDP Act compliance: verify no PII leaves HDFS without Ranger policy approval and Atlas audit trail

Create first customer compliance report: complete data lineage + access history for one dataset in 30 seconds

▸ MILESTONE: First DPDP-compliant dataset certified — Atlas lineage + Ranger policy + audit trail complete

WEEK 6 — Great Expectations + Data Quality Sigma  ·  Six Sigma: Measure + Analyse

Install Great Expectations 0.18 — initialise suite for each active Airflow DAG

Define expectations for 5 key datasets: null checks, range checks, referential integrity, schema validation

Integrate GE checkpoint into every Airflow DAG — pipeline fails automatically if data quality drops below threshold

Build Six Sigma dashboard in Apache Superset: sigma level per pipeline, defect rate trend, quality score history

Install Apache Superset 3.1 — connect to Presto as SQL source, Druid for real-time charts

Calculate baseline sigma level for each pipeline: record as the Six Sigma 'Define' benchmark

Set up automatic sigma level alerts: Slack notification when any pipeline drops below 4.5σ

Document first Six Sigma quality report — all pipelines with sigma levels, defect counts, and improvement actions

▸ MILESTONE: Six Sigma quality dashboard live — all pipelines showing real-time sigma scores

PHASE 3  Blockchain Lineage

Days 46–60  ·  Month 4

Goal: Hyperledger Fabric running — every Spark job, Airflow DAG run, and Hive transformation cryptographically hashed and recorded permanently.

WEEK 7 — Hyperledger Fabric Network  ·  Six Sigma: Control

Install Hyperledger Fabric 2.5 on 3 nodes (1 orderer, 2 peer organisations: DataNexus + Customer)

Create datanexus-channel — install and commit DataNexus Lineage chaincode

Lineage chaincode functions: LogTransformation(jobId, inputHash, outputHash, timestamp, owner)

Lineage chaincode functions: GetLineage(datasetId) — returns full transformation history

Lineage chaincode functions: VerifyIntegrity(datasetId, hash) — cryptographic proof check

Write Spark listener in Python: after every job, compute SHA-256 of output dataset, invoke Fabric chaincode

Write Airflow callback: on DAG success/failure, log run metadata + output hashes to Fabric ledger

Test: run 10 Spark jobs — verify all 10 appear on Hyperledger ledger with correct hashes

▸ MILESTONE: Blockchain lineage live — first tamper-proof audit trail of DataNexus pipeline runs

WEEK 8 — IPFS + Compliance Verification  ·  Six Sigma: Control

Install IPFS node on master: ipfs init && ipfs daemon

Write export function: dataset → IPFS pin → CID stored on Hyperledger alongside transformation hash

Build compliance verification CLI: datanexus verify --dataset sales_q4 — returns Fabric proof in seconds

Build compliance verification web UI in Superset: one-click audit report for any dataset

Simulate regulator audit: provide dataset CID + Fabric transaction ID — prove data integrity without exposing raw data

Document the DataNexus Data Passport: dataset ID, owner, quality score, lineage hash, IPFS CID — one JSON

Connect first pilot customer to Hyperledger Fabric network as read-only auditor node

Publish first blockchain-verified Six Sigma quality report — signed with Fabric certificate

▸ MILESTONE: First customer connected to Hyperledger — real blockchain-verified data audit delivered

PHASE 4  AI Layer + NLP Query Engine

Days 61–90  ·  Months 5–6

Goal: LLM-powered NLP queries in Telugu/Hindi/English, MLflow ML tracking, self-healing Airflow, Apache Druid real-time OLAP.

WEEK 9 — MLflow + Spark MLlib  ·  Six Sigma: Analyse + Improve

Install MLflow 2.10 — configure PostgreSQL backend, S3-compatible HDFS artifact store

Instrument every Spark MLlib training job with mlflow.spark.autolog() — zero code change needed

Build first DataNexus ML model: anomaly detection on pipeline metrics using Spark MLlib IsolationForest

Register model in MLflow Model Registry — deploy as REST API endpoint using MLflow serve

Connect anomaly detection model to Great Expectations — automatic sigma drop prediction 30 minutes in advance

Build churn prediction demo on sample customer data: Spark MLlib → MLflow → Superset dashboard

Set up MLflow experiment comparison UI — show to first pilot customer as DataNexus AI capability demo

WEEK 10 — Self-Healing Airflow Plugin  ·  Six Sigma: Improve

Build DataNexus Healing Plugin for Airflow: monitors task failures in real time via Airflow REST API

Failure pattern library v1.0: connection timeout (retry with backoff), schema mismatch (alert + quarantine), source unavailable (reroute to backup), out-of-memory (reduce batch size and retry)

Each fix attempt is logged to Hyperledger Fabric: what failed, what was tried, what was the outcome

If plugin cannot fix in 3 attempts: escalate to human with full diagnosis report via Slack/email

Test: deliberately break 10 different pipeline scenarios — verify plugin fixes 8/10 without human intervention

Calculate self-healing rate as a public metric: published on DataNexus status dashboard

Document first 'DataNexus healed itself' story for marketing and investor updates

▸ MILESTONE: Self-healing rate above 80% — pipelines fix themselves faster than humans could respond

WEEK 11-12 — NLP Query Engine + Apache Druid  ·  Six Sigma: Improve

Deploy Ollama with Llama 3.1 8B on master node (GPU optional — CPU inference sufficient for demo)

Build NLP-to-SQL pipeline: user input (any language) → Llama translation → Presto SQL → results

Build language detection layer: auto-detect Telugu, Hindi, Tamil, English, Kannada input

Test Telugu query: 'చివరి నెలలో అత్యధిక అమ్మకాలు ఏ ప్రాంతంలో జరిగాయి?' → correct Presto SQL → result

Test Hindi query: 'पिछले तिमाही में सबसे ज़्यादा बिक्री किस क्षेत्र में हुई?' → correct result

Install Apache Druid 28.0 — configure Kafka ingestion for real-time data (sub-second query latency)

Connect Druid to Superset — build live dashboard: sales by region updating every 5 seconds

Full demo pipeline: Telugu question → NLP → Presto SQL → Druid OLAP → Superset chart → in under 3 seconds

▸ MILESTONE: NLP query live — first demo of Telugu question answered by DataNexus in 3 seconds

PHASE 5  UI, Pilots & Public Launch

Days 76–90  ·  Months 7–9

Goal: React unified console, 3 signed pilot customers, GitHub open-source launch, public beta, seed funding closed.

WEEK 11 — Team Building + First Customers  ·  Six Sigma: Define

Hire: 2 senior Hadoop/Spark engineers (Hyderabad or remote India), 1 blockchain engineer (Hyperledger experience)

Hire: 1 DevOps/infra engineer for cluster automation, 1 enterprise sales lead (BFSI or government experience)

Target pilot customer segment 1: Indian private banks — DPDP Act compliance is urgent, budget is available

Target pilot customer segment 2: Indian manufacturing companies — supply chain data currently in 6+ tools

Target pilot customer segment 3: State government data departments — Digital India mandate driving urgency

Pilot offer: 90-day free deployment on customer's own hardware, DataNexus team installs and configures

Pilot commitment: customer provides 2 real pipelines to migrate from existing tools to DataNexus

First customer call goal: show live blockchain-verified compliance report — this closes pilots faster than any demo

▸ MILESTONE: 3 pilot customers signed — letters of intent in hand for first paying contracts

WEEKS 12-13 — React Console + Open Source Launch  ·  Six Sigma: Improve

Build DataNexus React console: unified login → pipeline dashboard → sigma scores → query console → audit trail

One login. One UI. Wraps: NiFi, Airflow, Presto, Superset, Atlas, Ranger, Hyperledger audit viewer

Publish DataNexus on GitHub: github.com/datanexus/core — Apache 2.0 license, full documentation

Write README that tells the founding story, the Manifest principles, and includes one-command cluster setup

Post launch announcement: LinkedIn, HackerNews, Data Engineering Slack communities, NASSCOM forums

Submit DataNexus to NASSCOM Emerge 50 — top 50 Indian tech startups programme

Apply for MeitY Startup Hub support — DataNexus qualifies under Digital India data infrastructure category

Publish first DataNexus blog post: 'Why we built a data platform guided by the Bhagavad Gita'

WEEK 13 — Seed Funding + 90-Day Close  ·  Six Sigma: Control

Prepare investor data room: pitch deck, Manifest document, 90-day plan, 3 pilot LOIs, sigma quality report

Target investors: Blume Ventures, Nexus Venture Partners, Stellaris Venture Partners (all India-focused, deep tech)

Target angels: senior data engineering leaders at Flipkart, Infosys, TCS, HDFC Bank

Schedule 10 investor meetings in Week 13 using warm introductions from pilot customers and NASSCOM network

Fundraise ask: ₹5 Crore / $600K seed — 60% engineering, 20% infrastructure, 20% GTM

Day 90 deliverable: DataNexus running in production at 1 pilot customer, 3 more in onboarding

Day 90 deliverable: GitHub repo with 100+ stars, 10+ contributors from open-source community

Day 90 deliverable: Seed round term sheet signed or in final negotiation

▸ MILESTONE: PUBLIC BETA LAUNCHED — DataNexus live, open source, pilots running, funding in progress

FIRST 14 DAYS — DAY BY DAY

The first two weeks set the entire trajectory. Do not skip any day.

DAY 1  Order/confirm 5 machines. Install Ubuntu 22.04. Create 'hadoop' user on all nodes. Configure /etc/hosts with all hostnames. Test ping between all nodes.

DAY 2  Install Java 11 on all nodes. Generate SSH keypairs. Configure passwordless SSH from NameNode to all DataNodes. Verify: ssh datanode1 from namenode with no password prompt.

DAY 3  Download Hadoop 3.3.6 tarball on all nodes. Set HADOOP_HOME, JAVA_HOME, PATH in ~/.bashrc. Copy hadoop-env.sh, core-site.xml, hdfs-site.xml from template.

DAY 4  Format NameNode: hdfs namenode -format. Start HDFS: start-dfs.sh. Verify all DataNodes at http://namenode:9870. Create base directories in HDFS.

DAY 5  Configure YARN: mapred-site.xml, yarn-site.xml. Start YARN: start-yarn.sh. Run MapReduce smoke test: hadoop jar hadoop-mapreduce-examples.jar pi 4 100.

DAY 6  Install Spark 3.5. Configure spark-env.sh with YARN master. Run: spark-submit --master yarn examples/pi.py. Verify output in YARN logs.

DAY 7  REST DAY — document what is built. Write the DataNexus cluster architecture diagram. Update the GitHub README draft. Review the Manifest. Plan Week 2.

DAY 8  Install Kafka 3.6 + ZooKeeper on 3 nodes. Create test topic. Produce and consume 1M messages. Measure throughput. Target: 100MB/s minimum.

DAY 9  Install NiFi 1.23. Build first flow: REST API → Kafka → HDFS. Test with live public API (weather API or currency API as data source). Verify data appears in HDFS.

DAY 10  Install Airflow 2.8 with PostgreSQL backend. Write first DAG: daily_hello_world. Schedule it. Verify it runs at scheduled time. Configure Slack alerts.

DAY 11  Install Hive 3.1. Create metastore database in PostgreSQL. Start Hive Metastore. Create external table over Day 9 HDFS data. Run first HiveQL query.

DAY 12  Install Presto (Trino 435). Configure Hive connector. Run first Presto query over Hive table. Test federated query joining HDFS data with external MySQL.

DAY 13  Build the first real DataNexus pipeline end to end: NiFi ingest → Kafka → Spark streaming → HDFS Parquet → Airflow daily job → Hive table → Presto query. This is the demo.

DAY 14  MILESTONE REVIEW DAY: Does the pipeline work end to end? Are all services running? Run the Phase 1 checklist. Record all sigma metrics from this week as the baseline. Brief the team. Celebrate — the foundation is built.

"Proceed. Build. Shake the world."

DataNexus  ·  datanexus.io  ·  Hyderabad, India  ·  2025